SE Project Management（SEPM）

Week 5 超詳細雙語筆記 Part 1（Information Radiator / Sprint Backlog / Kanban vs Scrum / Tools）

2026-03-04

# 1) 本週你要會什麼（Week 5 goals）

Explain what an Information Radiator is, why “there can be only one”, and what must be on it.

能解釋什麼是 Information Radiator、為何「只能有一個」，以及上面必須放什麼。

Build a sprint backlog correctly: PBI → tasks → owners → status, with the right level of detail.

能正確建立 sprint backlog：PBI→tasks→負責人→狀態，且細節程度剛好。

Understand sprint planning notes & retro notes: who writes them, when, how long, and what sections.

理解 sprint planning notes 與 retro notes：誰寫、何時寫、寫多長、包含哪些段落。

Compare Scrum vs Kanban and know when/why to combine (Scrumban).

能比較 Scrum vs Kanban，並知道何時/為何要混用（Scrumban）。

Choose tools (Trello vs Jira) based on needs, not fashion.

能用需求導向選工具（Trello vs Jira），不是跟風。

# 2) Information Radiator（資訊看板）—「只能有一個」的真正原因

An information radiator is a large, highly visible display of critical team information, updated continuously (often during daily stand-up).

Information radiator 是一個很大、很顯眼、展示團隊關鍵資訊的看板，會持續更新（常在 daily stand-up 更新）。

Why “there can be only one”:

為什麼「只能有一個」：

Single source of truth: avoids conflicting status across multiple boards.

單一真相來源：避免多個看板狀態互相矛盾。

Forces alignment: everyone talks about the same reality.

強迫對齊：大家討論的是同一個現實。

Reduces overhead: no double-updating.

降低成本：不用重複更新。

What belongs on the radiator (minimum):

看板至少要有：

Sprint Goal + sprint dates (start/end).

Sprint 目標 + 起訖日期。

Sprint Backlog board (Not started / In progress / Done).

Sprint backlog 看板（未開始/進行中/完成）。

Burndown / burnup or simple progress metric.

燃盡/燃起圖或簡單進度指標。

Top blockers / risks visible with owners.

前三阻塞/風險（含負責人）。

Common mistakes:

常見錯誤：

Board shows too much detail → no one reads it.

看板塞太多細節→沒人看。

Board is not updated daily → becomes fiction.

不每天更新→變成假資料。

Multiple boards in different tools → conflicting truth.

不同工具多個看板→多個真相。

# 3) Sprint Backlog（衝刺待辦）怎麼寫才算對？

Sprint backlog is NOT just a list of PBIs. It is PBIs + the plan (tasks) to deliver them within the sprint.

Sprint backlog 不是只列 PBIs，而是「PBIs + 交付計畫（tasks）」：你怎麼在本 sprint 把它做出來。

Correct structure:

正確結構：

PBI (user story) with AC → tasks (engineering steps).

PBI（故事＋AC）→ tasks（工程步驟）。

Tasks are small (<= 1 day ideally) and assigned to owners.

tasks 要小（理想 <= 1 天）且有負責人。

Statuses reflect reality (not wishful thinking).

狀態要反映現實（不是願望）。

What level of detail is “good enough”?

細到什麼程度才夠：

Good enough = enough to start work tomorrow with no confusion, but not so detailed that you waste time planning.

夠用 = 明天開始做不會混亂；但不需要細到你花太多時間規劃（那是浪費）。

Example task breakdown (one PBI):

Task 拆解示例（一個 PBI）：

Task 1: Define DB table/fields (schema).

Task 1：定義資料表/欄位（schema）。

Task 2: Build UI screen + validations.

Task 2：做 UI 畫面＋輸入驗證。

Task 3: Implement duplicate-check logic.

Task 3：實作重複資料檢查。

Task 4: Unit tests + AC verification.

Task 4：單元測試＋驗收標準驗證。

# 4) Sprint Planning Notes / Retro Notes：誰寫？何時寫？寫多長？

Who writes:

誰寫：

Scrum Master scribes the notes during the meeting (no extra time after).

Scrum Master 在會議中邊開邊記（不額外佔用會後時間）。

How long:

寫多長：

Short notes, max ~2 pages. Use short sentences; avoid long paragraphs. Proof-read.

短筆記，最多約 2 頁。短句、避免長段落、要校對。

Planning Notes sections (from workshop):

Planning Notes 段落（講義給的）：

1. Goal (what we aim to achieve).

1. Goal（本 sprint 想達成什麼）。

2. Duration (fixed: e.g., 2 weeks).

2. Duration（固定，例如 2 週）。

3. Vision for this sprint (what backlog items and why; shippable product).

3. Vision（選哪些 items＋原因；可交付成品長相）。

4. Estimation in story points + justification.

4. 點數估算＋理由。

Retro Notes sections (from workshop):

Retro Notes 段落（講義給的）：

Went well.

做得好的。

Could have gone better.

可以更好的。

Surprises.

意外/驚訝。

Lessons learned.

學到的教訓。

Final thoughts: keep/change.

結尾：保留/改變。

# 5) Kanban vs Scrum（以及 Scrum + Kanban）

Scrum: timeboxed sprints + roles + events + planned commitment.

Scrum：有固定 sprint + 角色 + 事件 + 承諾交付。

Kanban: continuous flow + WIP limits + manage cycle time.

Kanban：連續流動 + WIP 限制 + 管理 cycle time。

Scrumban: keep Scrum cadence but use Kanban board/WIP limits to improve flow.

Scrumban：保留 Scrum 節奏，但用 Kanban 看板/WIP 限制提升流動。

When to prefer Kanban:

何時更適合 Kanban：

Unplanned work (ops/support/bugs) dominates.

臨時工作（維運/支援/bug）佔比高。

Need to minimize cycle time and handle frequent small tasks.

需要降低 cycle time、常有小任務。

When to prefer Scrum:

何時更適合 Scrum：

Building product features with clear goals per sprint.

做產品功能，sprint 目標清楚。

Need regular stakeholder cadence (review/retro).

需要固定節奏跟利害關係人同步。

# 6) Trello vs Jira：怎麼選（別背工具名，背選擇理由）

Trello: simple, visual, low setup cost; good for small teams and simple workflows.

Trello：簡單直覺、設定成本低；適合小團隊/流程簡單。

Jira: powerful workflows, issue types, reports; good for larger teams/complex dependencies but higher overhead.

Jira：流程強、類型多、報表多；適合大團隊/相依複雜但成本較高。

Tool selection checklist:

工具選擇檢核：

Team size and complexity?

團隊規模與複雜度？

Need reporting (velocity, burndown, release)?

是否需要報表（velocity、燃盡、release）？

Need strict workflows/approvals?

是否需要嚴格流程/審核？

Setup time acceptable?

能接受的設定成本？

# 7) Flashcards（Q&A）

Q: Why only one information radiator?

A: Single source of truth; avoids conflicting status.

問：為何只能有一個資訊看板？

答：單一真相來源，避免狀態衝突。

Q: Sprint backlog vs product backlog?

A: Product backlog = what; sprint backlog = what + how (tasks) for this sprint.

問：產品待辦 vs 衝刺待辦？

答：產品待辦是做什麼；衝刺待辦是本 sprint 做什麼＋怎麼做。

Q: Who writes sprint notes?

A: Scrum Master during the meeting.

問：Sprint notes 誰寫？

答：Scrum Master 會中記錄。

Q: Scrum vs Kanban difference?

A: Scrum = timeboxed commitment; Kanban = flow + WIP limits.

問：Scrum vs Kanban 差別？

答：Scrum 以 sprint 承諾交付；Kanban 以流動＋WIP 控制。