SE Project Management（SEPM）

Week 4 超詳細雙語筆記 Part 2（Templates + Exercises + Workshop-ready Outputs）

2026-03-04

# 1) Rolling Wave Planning 模板（可直接交/可直接用）

How to write it in an assignment/report:

你在作業/報告可以直接這樣寫：

We adopt Rolling Wave Planning: maintain a high-level roadmap for the full project (milestones + assumptions), while elaborating detailed plans only for the next 1–2 sprints. We refine the plan at the last responsible moment based on new information (feedback, risks, dependency resolution).

我們採 Rolling Wave Planning：保留整體專案的高層 roadmap（里程碑＋假設），但只對接下來 1–2 個 sprint 做細部規劃；並在 last responsible moment 依新資訊（回饋、風險、相依性）更新計畫。

Mandatory elements checklist:

必備元素檢核：

High-level milestones for the whole project.

全專案高層里程碑。

Near-term detailed plan (next sprint) including tasks/owners.

近期（下一個 sprint）細部計畫（任務/負責人）。

Assumptions + dependencies explicitly listed.

假設＋相依性明列。

Risk register with triggers/mitigations.

風險登錄表（觸發/緩解）。

Replanning cadence (e.g., each sprint planning / weekly).

更新節奏（每次 sprint planning 或每週）。

# 2) Sprint 0 交付物清單（模板）

Sprint 0 goal:

Sprint 0 目標：

Make Sprint 1 delivery possible by creating the minimum foundations.

建立最小基礎，讓 Sprint 1 能交付。

Deliverables (copy/paste and customize):

交付物（可直接套用修改）：

Repo created; branching rules documented; basic CI pipeline runs on push.

建立 repo；分支規則文件化；基本 CI 在 push 時可跑。

Architecture sketch + key decisions (DB, hosting, auth, APIs).

架構草圖＋關鍵決策（DB/部署/登入/API）。

Definition of Done (DoD) draft + coding/testing standards.

DoD 草案＋coding/testing 標準。

Prioritized product backlog v1 with acceptance criteria for top items.

排序好的產品待辦 v1（前幾項含驗收標準）。

Risk register v1 + mitigation owners.

風險登錄表 v1＋緩解負責人。

# 3) 估算練習：點數怎麼估才合理（帶你做一遍）

Step 1: pick reference stories

步驟 1：選參考故事（anchor stories）

Define a 1-point story as “small, well-known, low-risk”. Define 5-point as “bigger or uncertain”.

把 1 點定義成「小、清楚、低風險」；5 點定義成「更大或更不確定」。

Step 2: estimate new story relative to anchors

步驟 2：用相對比較估新故事

If story is ~2× the effort/uncertainty of 2 points, it might be 3–5 points; discuss why.

如果新故事大約是 2 點故事的 2 倍工作量/不確定性，可能就是 3–5 點；要討論原因。

Step 3: if too big, split

步驟 3：太大就拆

Split by workflow, happy-path vs edge-case, or read-only vs write operations.

按流程切、先 happy path 再 edge cases、先只讀再可寫等方式拆分。

# 4) Scrum meetings 輸出範本（你交作業/做筆記要長這樣）

Sprint Planning output template:

Sprint Planning 輸出模板：

Sprint Goal: … (1–2 sentences)

Sprint Goal：…（1–2 句）

Selected backlog items: US-001, US-002, …

選定 items：US-001、US-002…

Capacity: team members × available hours; planned points <= capacity

容量：成員×可用工時；承諾點數<=容量

Task breakdown: item → tasks → owners → estimates

拆解：item→tasks→負責人→估算

Risks: top 3 + mitigation + trigger

風險：前三＋緩解＋觸發

Daily Scrum template (3 questions):

Daily Scrum 模板（三問）：

What did I do yesterday?

昨天我做了什麼？

What will I do today?

今天我會做什麼？

Any blockers?

有沒有阻塞？

Sprint Review output template:

Sprint Review 輸出模板：

Demo: what is working (with evidence).

Demo：哪些東西可用（附證據）。

What is not done / deferred.

哪些沒做完/延後。

Stakeholder feedback (bullet list).

利害關係人回饋（條列）。

Backlog changes (new items / reprioritization).

Backlog 變更（新增/改排序）。

Retro output template:

Retro 輸出模板：

Keep: …

保留：…

Stop: …

停止：…

Start: …

開始：…

Action items (1–3): owner + due date + success metric

行動項（1–3）：負責人＋期限＋成功指標

# 5) Exam traps（考點/陷阱）

Trap: “Rolling wave planning means no milestones.”

坑：以為滾動式規劃就不用里程碑。

Fix: You still need milestones/assumptions for the whole project; only details are deferred.

修正：里程碑與假設仍要有；延後的是細節。

Trap: “Sprint 0 means no deliverables.”

坑：以為 Sprint 0 不用交付物。

Fix: Sprint 0 deliverables are foundations (CI, backlog readiness, architecture decisions).

修正：Sprint 0 要交付的是基礎（CI、backlog readiness、架構決策）。

Trap: “Velocity is a target.”

坑：把 velocity 當 KPI 目標。

Fix: Velocity is a forecast input, not a performance target.

修正：velocity 用來預測，不是拿來逼績效。

# 6) Flashcards（Q&A）

Q: Why plan at the last responsible moment?

A: To reduce rework from wrong assumptions while still deciding in time.

問：為何要最後責任時刻才決策？

答：減少錯誤假設造成的返工，但仍確保不會拖到影響結果。

Q: What should Sprint 0 NOT become?

A: A big design phase with no feedback/delivery.

問：Sprint 0 不該變成什麼？

答：沒有回饋與交付的長期大設計階段。

Q: What is the best use of story points?

A: Relative estimation for forecasting and planning, not individual evaluation.

問：點數最好的用途？

答：做相對估算以利預測與規劃，不是個人考核。

Q: What are the key outputs of Sprint Planning?

A: Sprint Goal + Sprint Backlog + capacity-checked plan.

問：Sprint Planning 主要輸出？

答：Sprint Goal＋Sprint Backlog＋容量檢查後的計畫。